## Slide 1: Field Instruction Initiative Group Supervision Model
University of Southern California School of Social Work
Three Years of Implementation /2010-2013
Model Components
Mutual Partnership Activities
Field Curriculum
Presenters: Micki Gress, Ph.D. and Jolene Swain, MSW

## Slide 2: Problem Statement
Lack of consistency in addressing the CALSWEC competencies in the field
Field Instruction focused only on case supervision
Lack of Field Instructor (FI) time to supervise students
Student feelings of disconnect from the CalSWEC program and other CalSWEC students
USC CALSWEC field faculty desire to increase collaboration and support to FIs
Notes:   It was perceived that there is a lack of consistency in addressing the CALSWEC competencies field instruction provided to our CALSWEC students.
    Field Instruction was only focused on case supervision
    DCFS field instructors (FI) are not given release time to supervisor students so the amount of time the FI can spend in field instructing the student is limited to 1 hour per week
    CALSWEC students stated they did not feel connected to the CALSWEC program through their MSW program experience
    CALSWEC students did not feel that they had sufficient time to interact with other CALSWEC students in the program
    USC CALSWEC field faculty wanted to establish a stronger working relationship including providing additional support and better collaboration with CALSWEC field instructors (foundation/concentration year)

## Slide 3: Operating Theory of Change
Development of a group field instruction model and curricula that incorporate EPAS standards and CALSWEC competencies enhances learning experience to help students integrate theory and practice in child welfare
Integrative IV-E Field Seminars provide connection and support for students to each other and to the CalSWEC program, and opportunities to integrate theory and practice
Increased interactions with USC CALSWEC field faculty strengthen connections with the students
Notes:   We believe through the development of a group field instruction model and the development of curricula that incorporate both the EPAS standards and the CALSWEC competencies we could enhance the learning experience to help students better integrate theory and practice in child welfare.
  These seminars will provide the students with an opportunity to interact in a small group setting with the same group members and instructors throughout the MSW program, creating a strong support network. 3. In working with CALSWEC field instructions in the development of the circular collaboration with and support to these field instructors will be enhanced.
  Increased interactions with USC CALSWEC field faculty will strengthen connections with the students.
  These seminars will provide opportunity for the students to integrate their practice in the field placement with the EPAS standards and CALSWEC competencies.
  These seminars will allow students to learn and practice skills in a group supportive group setting; providing rich professional coaching opportunities.

## Slide 4: Operating Theory of Change (con’t)
Integration of: community providers/ consumers as guest lecturers; multi-media presentations; seminar instructors with PCW experience, enhance student learning.
Education and integration of FIs regarding the group seminar content allows for successful completion of field assignments
High ratio of number of instructors to students allows for rich coaching opportunities in learning new skills.
Notes:   It reinforces students’ commitment to the CALSWEC mission, and centralizes the importance of CALSWEC in the MSW program.
  Student learning will be enhanced through the integration of community providers and consumers as guest lecturers in the classroom.
  The use of multi media presentations greatly enhances student learning.
  It is important to educate field instructors regarding the group seminar content, in order for them to integrate this content and allow students to complete seminar assignments in the field placement.
  It is a critical component to the student’s learning that the seminar instructors act as mentors and role models and have extensive backgrounds in child welfare.
  The seminar instructor’s participation in the process exercises models the ability to risk in the classroom and enhances student learning.
  High ratio of number of instructors to students allows for rich coaching opportunities in learning new skills.

## Slide 5: Core Components/Activities
Integrated IV-E Field Seminars; one for foundation year students and one for concentration year students
  CALSWEC FI input and orientation to field curriculum
  FI commitment to supporting seminar field assignments
FI trainings/meetings facilitated by CALSWEC field faculty four times a semester
Field units
  Two DCFS concentration year student field units (pilot project initiated by DCFS in response to USC’s FII)
  Pilot foundation year student field unit in a community based child welfare agency for four students
Notes:   This project developed two integrated seminars; one delivered to foundation year students and one to concentration year students
  All CALSWEC Field Instructors were introduced to the curriculum by the CALSWEC field faculty and gave input into its development.
  Field Instructors agreed to facilitate students completing group seminar assignments in their field placements.
  Field Instructors trainings/meetings were facilitated by CALSWEC field faculty four times a semester. All concentration year students were placed in two DCFS student field unit (pilot project initiated by DCFS in response to USC’s FII). Four foundation year students were placed in a pilot student field unit in a community based child welfare agency.
  These seminars were designed to prepare students to provide appropriate social work services to clients in public child welfare, to analyze the strengths and barriers in the clients’ social systems and communities that are significant to helping clients achieve their goals, to think critically, to be self aware, to understand the impact of culture on behavior, and to integrate evidence based best practices in child welfare into their work with clients. This is accomplished through didactic, multi-media, case presentations, role play, and other experiential exercise as well sharing with consumers and public child welfare social workers.

## Slide 6: Key Implementers and Roles
USC CalSWEC Faculty/Staff
  Jolene Swain, MSW, CALSWEC Project Coordinator
  Dr. Micki Gress, CALSWEC Research Consultant
  Developed and delivered student field seminar and FI training curricula
CALSWEC Field Education Field Faculty
  Nancy Flax-Plaza, LCSW
  Rafael Angluo, LCSW
  Served as Field Liaisons, and co-taught student field seminar
CBO Intern Coordinator
  Stephanie Carter, MSW
  Supported development of field unit; trained and supported FIs
LA County DCFS Staff
  Maria Camarillo, MSW - Manager of Education and Licensure
  Elizabeth Romero, LCSW - CALSWEC Intern Coordinator/Field Instructor
  Robin Sims MSW - CALSWEC Intern Coordinator/Field Instructor
  Supported development of field unit.
Notes: CALSWEC Project Coordinator, Jolene Swain,MSW and the CALSWEC Research Consultant, Dr. Micki Gress developed the curriculum for the two group supervision seminars and for the field instructors trainings. They also delivered the curriculum to both students and field instructors. They collaborated with a local community-based agency and local county child welfare agency to develop field education units and to integrate agency field instruction and university- based group student supervision.
Nancy Flax-Plaza, LCSW, CALSWEC Field Education Field Faculty co-taught the Foundation Field Education Group Supervision Seminar and liaised the Foundation year students. Rafael Angluo, LCSW CALSWEC Field Education Faculty liaised the concentration year students.
Stephanie Carter, MSW, Foundation Community Based Agency Intern Coordinator supported the development of the student unit and coordinated/delivered the intern training and supervised the student’s field instructors.
Maria Camarillo, MSW, LA County DCFS Manager of Education and Licensure Elizabeth Romero, LCSW, LA County DCFS CALSWEC Intern Coordinator/Field Instructor and Robin Sims MSW, LA County DCFS CALSWEC Intern Coordinator/Field Instructor collaborated with the university's CALSWEC Program to develop and implement the concentration year field units. They supported and helped integrate the agency based field instruction and the university based group supervision.

## Slide 7: Evaluation Measures and Results
2013 Significant Field Instructor Results
  100% of Concentration Year (CY) and Foundation Year (FY) Field Instructors’ students know the dual mission of Public Child Welfare
  100% of CY and FY think that role playing helps students in learning how to work with clients however 100% of CY and FY Field Instructors reported they only seldom use role play in individual sessions with PCW students
  100% of CY stated they frequently engage in discussions around ethics and values; 75% of FY stated they frequently engage and 25% sometimes engage in discussions around ethics and values
  100% of CY frequently talk about the impact of working in diverse environments and how to work effectively in different communities with different clients; 50% of FY Field Instructors talked frequently about this and 50% reported sometimes talking to their students about these issues.
  50% of CY taught their students how to do culturally sensitive interviewing, 50% did not; 75% of FY taught their students this and 25% did not.
  100% of CY discussed Katie A with students; 25% of FY discussed Katie A and 75% did not
  50% of CY and FY discussed and taught evidence-based practice with students and 50% of CY and FY did not.
  100% of CY and FY integrated Motivational Interviewing skills in their work with their students
  100% of CY and FY taught students how to conduct strength based needs assessments
  50% of CY and FY helped students integrate attachment theory into their work with clients; 50% of Cy and FY did not.
  100% of CY exposed students to other DCFS workers; 75% of FY did this and 25% did not
  100% of CY and FY reported it was very important to help students develop a peer network that will extend into their employment at DCFS

## Slide 8: Evaluation Measures and Results
2011-2012 & 2012-2013 Significant Student Satisfaction Survey Results
  93% of the 2011-2012 cohort and 100% of the 2012-2013 cohort reported knowing the dual mission of Public Child welfare
  100% of both cohorts thought that role playing/case discussions helped them identify value dilemmas in their work with clients.
  100% of the 2011-2012 cohort and ; 93% of the 2012-2013 cohort learned about diversity and their values/believes around diversity
  93% of the 2011-2012 cohort and 100% of the 2012-2013 cohort understood the interface between mental health and public child welfare, and the possible cracks in the system.
  85% of the 2011-2012 cohort and 100% of the 2012-2013 stated they have a better understanding of evidence based practice as a result of this seminar.
  100% of both cohorts stated they understand the purpose and foundations of motivational interviewing.
  93% of the 2011-2012 cohort and 100% of the 2012-2013 cohort stated they have a better understanding of the importance of strength based assessment.
  93% of the 2011-2012 cohort and 100% of the 2012-2013 cohort reported having a better ability to perform strength based assessments.
  100% of both cohorts stated they understand attachment as it relates to work in public child welfare.
  85% of the 2011-2012 cohort and 100% of the 2012-2013 cohort reported that working in a small seminar group enhanced their education very much.
  77% of the 2011-2012 cohort and 100% of the 2012-2013 cohort reported that working in a small seminar groups helped them very much to develop a support network with other students.
  85% of the 2011-2012 cohort and 100% of the 2012-2013 cohort stated that this seminar helped them to see and understand different points of view.

## Slide 9: Lessons Learned
Importance of:
  Strong relationships with agency partners and to involve them in the development/delivery of the curriculum
  Agency social workers as guest lecturers to present on specialized topics in the field seminar
  Time and opportunity to practice skills development through role play, case presentations, experiential exercises and class discussions
  Addressing core child welfare practice strategies, evidence based interventions in a team- and strengths-based approach
  Examination of professional values and ethics
  Continuously building cultural competency
  Introducing students to the social, economic , and political constructs of institutional racism and the impact on the public child welfare systems policies and practices
  Support network among the CALSWEC students and CALSWEC faculty.
  Co-teaching model with intensive coaching/mentoring, modeling for collaboration and conflict resolution, and demonstration of different styles and view points on the same issues.
Notes: Important to have strong relationships with agency partners and to involve them in the development/delivery of the curriculum
Important to have agency social workers come in to be guest lectures to present on specialized topics in the group supervision seminar
Important to allow students adequate time to process issues in class and to practice skills development through role play, case presentations, experiential exercises and class discussions.
Important to conceptually address the cores practice strategies (engagement, assessment, intervention, planning, and evaluation) in a team based strength- based approach including the consumer, the agency, the workers, the family, and the community.
Critical to integrate the examination for professional values and ethics in classroom discussion particularly as it relates to the development of professional self and the ability to strategize on how best to advocate for your client.
Continuously building cultural competency through self examination of one’s own cultural beliefs, values, and practices and the exposure to the histories of different racial and cultural groups.
Important to introduce students to the social, economic , and political constructs of this country and the institutional racism and the impact of these on the public child welfare systems policies and practices.
Importance of introducing best practices and evidence based interventions in public child welfare
Importance of nurturing the development of a support network among the CALSWEC students and CALSWEC faculty.
Importance of recognizing that the co-teaching model allows for intensive coaching/mentoring, modeling for collaboration and conflict resolution, and demonstration of different styles and view points on the same issues.

## Slide 10: Project Successes
CALSWEC students (Foundation/Concentration)
Elizabeth Romero, MSW
Nina Powell-McCall, MSW
Maria Camarillo, MSW